## Slide 1
Start-up phase
Goals Specifications
Tasks
Teambuilding Responsibility
Planning phase
Schedules Budgets
Resource allocation Risk management
Staffing
Supplier selection
Execution phase
Project control and status reports Changes
Prognoses Quality
Closure phase
Training of users Documentation
Release workers
Evaluation Learning and experience transfer
Time
Level of effort
Figure 1.1

## Slide 2
Project management
Execution
Input/ resources
Output/ results
Project work
Stakeholders and environment
Figure 1.2

## Slide 3
Planning
and organizing
Defining the goal
Monitoring and controlling
Execution
Input
Results
- Measure deviation
- Corrective actions
1
2
3
4
Figure 1.3

## Slide 4
Time
Cost
Quality
Time
Cost
Scope
Quality
Cost
Quality
Scope
Time
Alternative A
Alternative B
Alternative C
Figure 1.4

## Slide 5
Operation
Main project
Pre-project
Pre-study
Decision:
Proceed or stop
Decision:
Proceed or stop
Figure 1.5

## Slide 6
Procurement
phase
Definition phase
Concept phase
Idea phase
Transfer to operation phase
Figure 1.6

## Slide 7
Procurement
Engineering
FEED
Concept
Completion
Construction
Figure 1.7

## Slide 8
Define the
project
Plan and organize
Execute
Complete/ closure
Corrections
Figure 1.8

## Slide 9
Brain-storming
Idea
develop-ment
Business case
Develop-ment
Testing
Launch
Gate 1
Gate 2
Gate 3
Gate 4
Gate 5
Figure 1.9

## Slide 10
Defining the requirement
Designing
Developing
and unit testing
Integrating and system testing
Implementing
and operating
Figure 1.10

## Slide 11
Identifying system
requirements
Designing
Developing
Testing
Figure 1.11

## Slide 12
Identifying system
requirements
Designing
Developing
Testing
Figure 1.11

## Slide 13
Waterfall -
One large delivery at the end
Spiral model/Scrum -
Many smaller deliveries along the way
Figure 1.12

## Slide 14
Project Proposal Form
Date: Name: Project name:
Project type: Internal project: External project:
Project purpose (expected benefits/value):
Strategic fit:
Project output (delivery):
Consequences if the project doesn’t start:
Critical project risks:
Project success criteria:
Estimated project cost:
Estimated project duration:
Internal resources needed: Yes No
Are these internal resourced available: Yes No
Approved: Yes No
Signature: Date:
Figure 2.1

## Slide 15
Organization’s
strategy
Analysis and project selection
Project execution
Use of the results/outputs
Financial
assessments
Strategic assessments
Technical assessments
Risk assessments
Feasibility assessments
Figure 2.2

## Slide 16
Resources (inputs)
Project goal (outputs)
Project purpose
Business or society goal
Operative
level
Strategic level
Level 4
Level 3
Level 2
Level 1
Figure 2.3

## Slide 17
Figure 2.4

## Slide 18
Investment
cost
Time
Net cash flow
Discounting
Year 0
Figure 2.5

## Slide 20
Pearl
Oyster
Bread and butter
White elephants
Potential profit or value
Probability of success
A
Low
Low
High
High
B
D
C
Figure 2.6

## Slide 21
Start
End
Time
Project
Identify benefits
Benefits realization
Figure 2.7

## Slide 22
Project owner’s responsibility
Project manager’s responsibility
Stage 1
Stage 2
Stage 3
Benefits planning
Benefits monitoring
Benefits
realization
Figure 2.8

## Slide 23
New university campus
Needs – admin. staff
Needs – scientific staff
Needs – students
Needs – under- graduate students
Needs – graduate students
Needs – PhD students
Needs – other stakeholders
Figure 3.1

## Slide 24
Time
Accumulated cost
Influence on the project
High
Low
Available
information
Strategic
period
Figure 3.2

## Slide 25
Program
Business strategy
5–10 years
Project
Project objective
9–18 months
Subproject
Major deliverables
6–12 months
Work package
Milestones
1–3 months
Activity
Measurable result
1–3 weeks
Task
Major workload
Days
Level
Purpose
Time horizon
Figure 3.3

## Slide 26
New house project
Site preparation
Excavation and grading
Foundation and footing
Utilities installation
Structure
Framing
Roofing
Windows and doors
Exterior (siding, paint)
Interior
Plumbing
Electrical
Insulation
Flooring
Paint and wall finishes
Landscaping and outdoor
Paths and driveways
Planting and lawn
Fencing and gates
Testing and inspection
Testing of all systems
Inspection with the contractor
Figure 3.4

## Slide 27
TechUpgrade
project
Implementation of new computer system
Technical installation of infrastructure
Technical installation of software
Organizational implementation of system
Training
Needs assessment
Development of training materials
Delivery of training
Organizational changes
Needs assessment
Planning for changes
Implementation of changes
Evaluation of changes
Figure 3.5

## Slide 28
START
CLOSURE
Project
One large output and delivery
Achievement of goal
Time
START
CLOSURE
Project
Several smaller outputs and deliveries
Achievement of goal and purpose while project is ongoing
Several smaller deliveries during the project
One large delivery at the end of the project
Achievement of purpose and
benefits realization can start
Figure 3.6

## Slide 29
Cost
Time
Quality
Free
Optimize
Fixed
Figure 3.7

## Slide 30
Cost
Time
Quality
Free
Optimize
Fixed
Figure 3.8

## Slide 31
Low
High
High
Directive behavior
Supportive behavior
LEADERSHIP STYLES
Delegating
S1
S2
S3
S4
Supporting
Coaching
Directing
Figure 4.1

## Slide 32
Transformational leadership The project manager inspires and motivates team members
Transactional leadership Use of incentives to create expected actions
Active leadership Proactive and prevents faults and mistakes from occuring
Passive leadership The project manager only acts when faults are discovered
Laissez faire leadership The project manager does as little as possible
Effective leadership
Non-effective leadership
Passive leadership
Active leadership
Figure 4.2

## Slide 33
Autocratic
Well meaning
autocratic
Consulting
Participating
The project manager makes the
decision and announce it
The project manager sells the decision
The project manager put forward his
ideas and ask for questions
The project manager propose a decision which can be changed
The project manager presents the problem, recieve alternative solutions, and make a decion
The PM sets the limits and asks for the team to make a decision
The team members are empowered to make their own decisions
Autocratic leadership style
Democratic leadership style
Figure 4.3

## Slide 34
Upwards – relation with the owner
Outwards – relation with the end users
Forwards – project planning
Backwards – project control
Inwards – evaluate own performance
Downwards – relation with the project team
Figure 4.4

## Slide 35
Level of collaboration
Level of self-interest
Tvang
Analytisk
tilnærming
Tilbake
-
trekking
Overglatting
Kompromiss
Low
High
High
Forcing
Collaborating
Withdrawal
Smoothing
Low
Compromising
Figure 4.5

## Slide 36
Project
A
Project
B
Project
C
Figure 4.6

## Slide 37
Project
Project
Project
P
Project
Project
Program
P
P
P
Project
Project portfolio
Project
Figure 4.7

## Slide 38
Goals
Projects
A single
project
Project
portfolio
Project program
Figure 4.8

## Slide 39
Line manager
Line manager
Line manager
CEO
Project A
Project B
Chief project officer
Figure 4.9

## Slide 40
Line organization
Project
Figure 5.1

## Slide 41
Functional
structure
Matrix
structure
Independent
structure
Figure 5.2

## Slide 42
CEO
Department 1
(line manager)
Department 2
(line manager)
Department 3
(line manager)
Project
A
Project
B
Figure 5.3

## Slide 43
CEO
Department 1
(line manager)
Department 2
(line manager)
Department 3
(line manager)
Project A
Project B
Figure 5.4

## Slide 44
Project manager
Line manager
100%
100%
0%
0%
Strong matrix
Weak matrix
Figure 5.5

## Slide 45
CEO
Department 1
(line manager)
Department 2
(line manager)
Department 3
(line manager)
Project
A
Project
B
Figure 5.6

## Slide 46
CEO
Personnel
Product development
Finance and accounting
Production
IT
Procurement
Marketing and sales
TechUpgrade
ProMetal
Figure 5.7

## Slide 47
The team’s development over time
Team efficiency
Low
Medium
High
Forming
Storming
Norming
Performing
Adjourning
Figure 5.8
Time

## Slide 48
Project manager
Ass. project
manager
Ass. project manager
Team
leader
Team
leader
Team
leader
Team
leader
Team
member
Team
member
Figure 5.9

## Slide 49
Report
(Project manager coordinates and integrates)
Chapter 2
Person B
Chapter 1
Person A
Chapter 3
Person C
Chapter 4
Person D
Chapter 2
Person B
One team:
Chapter 2
Person B
Chapter 1
Team A
Chapter 3
Team C
Chapter 4
Team D
Chapter 2
Team B
Several teams:
Report
(Project manager coordinates and integrates)
Figure 5.10

## Slide 50
Chapter 1
Chapter 2
Chapter 3
Chapter 4
Project manager
(coordinates)
Expert A
Expert B
Expert C
Figure 5.11

## Slide 51
Chapter 1
Chapter 2
Chapter 3
Chapter 4
Person A
Person B
Person C
Person D
Figure 5.12

## Slide 52
Chapter 1
Chapter 2
Chapter 3
Chapter 4
Person A
Technical support
Surgeon (main author)
Person C
Administrative support
Person D
Administrative support
Person B
Technical support
Figure 5.13

## Slide 53
IT
5 persons
Project manager
(management and coordination)
Finance and accounting
2 persons
Production
1 person
New computer system
Training
Organizational changes
Figure 5.14

## Slide 54
Project owner
Steering committee
Project manager
Reference group
Subproject
A
Subproject
A
Subproject
A
Figure 5.15

## Slide 55
CEO MetTech
Steering committee
Project manager: Peter
Reference group
New computer system
Team leader: Anne
Training
Team leader: Tom
Organizational changes
Team leader: Paul
Figure 5.16

## Slide 56
Activity 1
Activity 2
Activity 3
Activities
Persons
Project manager
Team member A
Team member B
Steering committee
Activity 4
A
A
A, R
A
R
R
C
I
R
R
D
Figure 5.17

## Slide 57
Contract
Project
Supplier
Figure 6.1

## Slide 58
Pre-qualification
Most economically
advantageous tender
Lowest
price
Produce
In-house
Direct purchase
Tender
competition
Negotiated
contract
Functional
requirements
Technical
requirements
PPP/BOT
Design &
build
Prime
contract
Multiple design & build
Multiple prime contracts
Fixed
price
Unit
price
Cost
plus
Incentives
Standard
contract terms
Special
contract terms
Payment during
operation
Pre-qualification
Award criteria
Contracting
Requirements
Contract structure
Payment terms
Incentives
Contract terms
Figure 6.2

## Slide 59
Client organization
Contracting organization
Decision to subcontract
all or part of the project
Invitation to tender
Decide to tender
Plan and estimate
Tender (bid)
Tenders received and evaluated
Short list/winning bid chosen
Negotiations
Signing of the contract
Meetings (question/answer)
Pre-qualification
Questions, interview, visits
Figure 6.3

## Slide 60
Specifications/ engineering/ design
Invitation to
tender
Chose lowest bid (price)
Tenders
received
Production/ construction
starts
Supplier chosen
Figure 6.4

## Slide 61
Invitation to
tender
Tenders
received
Contract signed
Evaluate tenders and
negotiate
Detailed design
and engineering
Supplier chosen
Production/ construction
starts
Figure 6.5

## Slide 62
Client
Supplier (design/build)
Subsupplier
Subsupplier
Subsupplier
Figure 6.6

## Slide 63
Client
Contractor (build)
Subcontractor
Subcontractor
Architect (design)
Figure 6.7

## Slide 64
Client
Construction
manager
Prime
contractor
Prime
contractor
Architect (design)
Prime
contractor
Subcontractor
Subcontractor
Figure 6.8

## Slide 65
Cost plus
Unit price
Fixed price
Low
High
Client’s risk
High
Low
Supplier’s risk
Figure 6.9

## Slide 66
Project costs
Target price
Lower costs than target price gives the supplier profit
Max profit supplier
Max extra costs supplier
Higher costs than target price
Gives the supplier extra costs
0
Profit
Increased costs
x
y
Figure 6.10

## Slide 67
Meeting notice
A project meeting will be arranged at BI Nydalen, room A3-109, September 13, 10am.
Invited: Per Olsen, Arne Strøm, Ole J. Larsen,
Mona Egge, Jan Holst, Elise Svendsen
Purpose: Identify, assess, and choose a research project
Agenda: 10.00-10.15 Welcome and introduction
10.15-11.00 Brainstorming
11.00-12.00 Lunch
12.00-12.50 Discussion
13.00-13.30 Choosing research project
Figure 7.1

## Slide 68
Thoughts (mental)
Worries
Negative self-talk
Unorganized thoughts
Wrong decisions
Nightmares
Anxiety and frustration
Feelings (emotional)
Loss of self-confidence
Poor self-image
Irritable
Depressed
Apathy and indifference
Disengagement
Physical (body)
Tired
Headaches
Muscle pains
Breathing problems
Heart palpitations
Burnout
Behavior
Restless
Loss of appetite
Smokes more
Drinks more alcohol
Sleeping problems
Increased sickness
Figure 7.2

## Slide 69
Feedback
Sender
Message
Channel
Receiver
Coding
Decoding
Noice
Figure 7.3

## Slide 70
Line
manager
Line manager
Line
manager
CEO
Project A
Project B
Project owner
PMO
Figure 7.4

## Slide 71
Value
delivery
Value
delivery
Value
delivery
Requirements
Design
Development
Testing
Implementation
One big value
delivery at the end
Waterfall
Agile
Figure 7.5

## Slide 72
Produkt backlog
Sprint planning
Sprint
backlog
Sprint review,
demonstration of new functionallity
Sprint
retrospective
Daily scrum
Sprint
Figure 7.6

## Slide 73
User story 1
User story 2
User story 3
User stories
Not started
In progress
Completed
Tasks
Task
Task
Task
Task
Task
Task
Task
Task
Task
Task
Task
Task
Task
Task
Figure 7.7

## Slide 74
Tasks
2
4
6
8
0
12
10
2 May
4 May
6 May
8 May
10 May
12 May
14 May
16 May
Ideal (the remaining tasks)
Actual (the remaining tasks)
Figure 7.8

## Slide 75
Project
Client
Users
Contractors
Consultants
Unions
Line
organization
Public authorities
Banks
Insurance
company
Certification institution
Press/media
Competitors
Other interest
groups
Technological
factors
Labor-related factors
Physical
factors
Economic
factors
Cultural
factors
Sustainability
factors
Political
factors
Stakeholders
Environmental factors
Figure 8.1

## Slide 76
E39 Highway
Stortinget
Agder county
Kristiansand municipality
Lindesnes municipality
Ministry of Climate and Environment
Ministry of Transport
Agder
county (adm.)
Statnett
Auditor General
The Norwegian Public Roads Adm.
County Governor
Ministry of Industry
The Norwegian Labour Inspection Authority
Ministry of Finance
Ministry of Local Government
Ministry of Transport
Ministry of Agriculture
Others
Neighbors
Naturvern- forbundet
Truck owners’ association
Nature and Youth
Toll companies
Press/media
(newspapers, radio and tv)
Car drivers
Local farmers
NHO
AF-Gruppen
Political stakeholders
Public agencies and authorities
Other stakeholders
Main contractors and sub-contractors
Norconsult
Asplan Viak
Other consultant companies
Consultants
Hæhre
TT Anlegg
Rambøll
Traftec
Sweco
Kruse Smith Entreprenør
Ribe Betong
Repstad Anlegg
Nomeland Maskin
Other sub-contractors
Norwegian Food Safety Authority
Others
Local Fire Brigades
NVE
The Norwegian Trekking Association
Local forest owners’ associations
Miljøvern- forbundet
Bird clubs
Local merchant associations
Commuter associations
Petrol stations
Bus companies
Norwegian agrarian association
Local political groups
Multiconsult
The Norwegian Coastal Adm.
Agder Energi
Local companies
Scout groups
Figure 8.2

## Slide 77
Startup
Identifying the stakeholders
Analyzing the stakeholders
Strategy and action
Follow-up
Stage 1
Stage 2
Stage 3
Stage 4
Stage 5
Communication and documentation
Figure 8.3

## Slide 78
Figure 8.4
Mixed blessing
Supportive
Non-supportive
Marginal
High
High
Low
Low
Stakeholder’s potential power to
influence or affect the project
Stakeholder’s willingness to collaborate with the project

## Slide 79
Strengths
Weaknesses
Opportunities
Threats
Negative values
Positive values
Past and present
Future
Figure 8.5

## Slide 80
1.
4.
3.
5.
2.
7.
6.
High
power
Low
power
8
7
6
5
4
3
2
1
10
9
1
2
3
4
5
6
7
8
9
10
Low
interest
High
interest
Stakeholders
Competitors
Volunteers
Audience
Sponsors
Media/press
Public authorities
Neighbors
Figure 8.6

## Slide 81
Figure 8.7
Collaborate
Involve
Defend
Monitor
Stakeholder’s potential power to
influence or affect the project
High
High
Low
Low
Stakeholder’s willingness to collaborate with the project

## Slide 82
Classic market
Through a third party
Open and direct
Integrated team
Partnering
Figure 8.8

## Slide 83
Classic market
Through a third party
Open and direct
Integrated team
Partnering
Degree of collaboration
High
Low
Figure 8.9

## Slide 84
The planning process
Inputs:
Resources
Information
Control mechanisms:
Standards
Procedures
Norms
Law and instructions
Budgets
Available time
Support and knowledge:
Tools and techniques
Software
Project manager and team members
Project office
Output/results:
Project plans
Figure 9.1

## Slide 85
Training
(T)
Implementing the data system
(I)
Organizational
changes
(O)
T1
I1
I2
I3
I4
T2
T3
O1
O2
I5
Activities
Result
path
Figure 9.2

## Slide 86
M2
M4
M3
M1
Work package level
Activity level
Task level
Figure 9.3

## Slide 87
A
B
D
C
E
Activity
1
3
4
2
5
A
B
C
D
E
Activity
AON network
AOA network
Figure 9.4

## Slide 88
ES
N
EF
t
FL
LS
LF
Early Finish
Float/Slack
Late Finish
Early Start
Identification no.
Late Start
Duration or time
Figure 9.5

## Slide 89
0
10
A
10
0
0
10
10
18
B
8
0
10
18
10
16
C
6
4
14
20
18
28
E
10
0
18
28
18
26
F
8
2
20
28
10
27
D
17
1
11
28
28
38
G
10
0
28
38
Figure 9.6

## Slide 90
o
m
p
Optimistic
Most likely
Pessimistic
Time
Figure 9.7

## Slide 91
o + 4m + p
6
E (t) =

## Slide 92
0
5
A
5
0
0
5
5
12
B
7
1
6
13
5
10
C
5
0
5
10
12
16
D
4
1
13
17
10
17
E
7
0
10
17
17
20
F
3
0
17
20
Figure 9.8

## Slide 93
Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
A |  |  |  |  |  |  |  |  |  | 
Days
Planned duration
Actual progress
Figure 9.9

## Slide 94
Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
B |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
C |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
E |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
F |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Days
Figure 9.10

## Slide 95
Time (weeks)
Costs (1000)
1
2
3
4
5
6
10
20
30
40
Crash costs
Normal
costs
Normal time
Crash time
Figure 9.11

## Slide 96
0 |  | 3
A | 3 | 0
0 |  | 3
3 |  | 7
B | 4 | 0
3 |  | 7
7 |  | 12
D | 5 | 0
7 |  | 12
7 |  | 11
E | 4 | 1
8 |  | 12
3 |  | 6
C | 3 | 2
5 |  | 8
12 |  | 16
F | 4 | 0
12 |  | 16
11 |  | 15
G | 4 | 1
12 |  | 16
16 |  | 16
Du | 0 | 
16 |  | 16
Figure 9.12

## Slide 97
0 |  | 3
A | 3 | 0
0 |  | 3
3 |  | 5
B | 2 | 1
3 |  | 6
6 |  | 10
D | 4 | 0
6 |  | 10
3 |  | 6
C | 3 | 0
3 |  | 6
10 |  | 12
E | 2 | 0
11 |  | 13
10 |  | 13
F | 3 | 0
10 |  | 13
13 |  | 17
G | 4 | 
13 |  | 17
Figure 9.13

## Slide 98
0 |  | 3
A | 3 | 0
0 |  | 3
3 |  | 5
B | 2 | 1
3 |  | 6
6 |  | 9
D | 3 | 0
6 |  | 9
3 |  | 6
C | 3 | 0
3 |  | 6
9 |  | 10
E | 1 | 0
9 |  | 10
9 |  | 10
F | 1 | 0
9 |  | 10
10 |  | 13
G | 3 | 
10 |  | 13
Figure 9.14

## Slide 99
Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
A |  |  |  |  |  |  |  |  |  |  |  |  | 
B |  |  |  |  |  |  |  |  |  |  |  |  | 
C |  |  |  |  |  |  |  |  |  |  |  |  | 
D |  |  |  |  |  |  |  |  |  |  |  |  | 
E |  |  |  |  |  |  |  |  |  |  |  |  | 
F |  |  |  |  |  |  |  |  |  |  |  |  | 
G |  |  |  |  |  |  |  |  |  |  |  |  | 
Days
Figure 9.15

## Slide 100
To Do
In Progress
(2)
Done
Figure 9.16

## Slide 101
To Do
In Progress
Done
Oppgave
Utført av
Milestones
Milestone 1
Oppgave
Utført av
Oppgave
Utført av
Oppgave
Utført av
Oppgave
Utført av
Oppgave
Utført av
Milestone 2
Milestone 3
Oppgave
Utført av
Oppgave
Utført av
Oppgave
Utført av
Oppgave
Utført av
Oppgave
Utført av
Oppgave
Utført av
Oppgave
Utført av
Oppgave
Utført av
Oppgave
Utført av
Oppgave
Utført av
Oppgave
Utført av
Oppgave
Utført av
Oppgave
Utført av
Oppgave
Utført av
Figure 9.17

## Slide 102
Backlog
Story 1
A
B
E
D
C
I
J
K
L
H
F
G
Selected
(2)
Development (3)
Ongoing
Done
Testing
(2)
Deploy
(1)
Complete
M
N
Figure 9.18

## Slide 103
Proposal estimate
Preliminary estimate
Substantive estimate
Definitive estimate
Actual costs
Inaccuracy of estimates
+
_
Time
Figure 10.1

## Slide 104
Project
Subproject
Subproject
Customer
Work package
Work package
Bottom-up
Project manager,
team leaders, and team members
estimate the costs for
tasks and activities
Total cost is found
by aggregating
all the cost estimates
at lower levels
Top-down
Customer or top management
set the budget
Project manager
allocates the budget
to subprojects,
work packages, etc.
Figure 10.2

## Slide 105
Direct
costs
Indirect
costs
Profit
Total costs
Base cost estimate
(baseline)
Contingency
Figure 10.3

## Slide 106
Activities
Cost
Cost
Cost
Cost
Cost
Cost
Cost
Contracts
Subprojects
Cost
Cost
Cost
Work packages
Project
Labor xxxx
Equipment xxxx
Materials xxxx
Other xxxx
Sum xxxx
Figure 10.4

## Slide 107
Project costs
230,000
250,000
290,000
P15
P40
P90
Figure 10.5

## Slide 108
Direct costs
Indirect costs
Profit
Total costs
Base cost estimate
(baseline)
Contingency reserve
Management reserve
Project budget
Figure 10.6

## Slide 109
A
C
E
B
D
A
B
C
D
E
Alt. A
Alt. B
Figure 11.1

## Slide 110
Design
Develop
Test
Figure 11.2

## Slide 111
0 |  | 0
Du | 0 | 
0 |  | 0
0 |  | 5
A | 5 | 0
0 |  | 5
0 |  | 3
B | 3 | 2
2 |  | 5
0 |  | 2
C | 2 | 6
6 |  | 8
5 |  | 8
D | 3 | 0
5 |  | 8
5 |  | 7
E | 2 | 3
8 |  | 10
8 |  | 10
F | 2 | 0
8 |  | 10
10 |  | 10
Du | 0 | 
10 |  | 10
Figure 11.3

## Slide 112
Activity/Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
A |  |  |  |  |  |  |  |  |  | 
B |  |  |  |  |  |  |  |  |  | 
C |  |  |  |  |  |  |  |  |  | 
D |  |  |  |  |  |  |  |  |  | 
E |  |  |  |  |  |  |  |  |  | 
F |  |  |  |  |  |  |  |  |  | 
Figure 11.4

## Slide 113
A
B
C
D
E
F
Workers
Weeks
1
2
3
4
5
6
7
8
9
10
1
2
3
4
5
6
Figure 11.5

## Slide 114
A
B
C
D
E
F
Workers
Weeks
1
2
3
4
5
6
7
8
9
10
1
2
3
4
5
6
Figure 11.6

## Slide 115
Resources
Time
Overload
Resource limit
Figure 11.7

## Slide 116
0 |  | 2
A | 2 | 0
0 |  | 2
10 |  | 12
H | 2 | 0
10 |  | 12
2 |  | 4
B | 2 | 0
2 |  | 4
4 |  | 6
C | 2 | 0
4 |  | 6
6 |  | 10
E | 4 | 0
6 |  | 10
2 |  | 4
D | 2 | 2
4 |  | 6
4 |  | 8
G | 4 | 2
6 |  | 10
4 |  | 6
F | 2 | 4
8 |  | 10
Figure 11.8

## Slide 117
Activity/Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
A | 5 | 5 |  |  |  |  |  |  |  |  |  | 
B |  |  | 4 | 4 |  |  |  |  |  |  |  | 
C |  |  |  |  | 2 | 2 |  |  |  |  |  | 
D |  |  | 3 | 3 |  |  |  |  |  |  |  | 
E |  |  |  |  |  |  | 1 | 1 | 1 | 1 |  | 
F |  |  |  |  | 3 | 3 |  |  |  |  |  | 
G |  |  |  |  | 2 | 2 | 2 | 2 |  |  |  | 
H |  |  |  |  |  |  |  |  |  |  | 3 | 3
Sum workers | 5 | 5 | 7 | 7 | 7 | 7 | 3 | 3 | 1 | 1 | 3 | 3
Figure 11.9

## Slide 118
Activity/Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
A | 5 | 5 |  |  |  |  |  |  |  |  |  | 
B |  |  | 4 | 4 |  |  |  |  |  |  |  | 
C |  |  |  |  | 2 | 2 |  |  |  |  |  | 
D |  |  |  |  | 3 | 3 |  |  |  |  |  | 
E |  |  |  |  |  |  | 1 | 1 | 1 | 1 |  | 
F |  |  |  |  |  |  | 3 | 3 |  |  |  | 
G |  |  |  |  |  |  | 2 | 2 | 2 | 2 |  | 
H |  |  |  |  |  |  |  |  |  |  | 3 | 3
Sum workers | 5 | 5 | 4 | 4 | 5 | 5 | 6 | 6 | 3 | 3 | 3 | 3
Figure 11.10

## Slide 119
10 |  | 14
F | 4 | 0
10 |  | 14
7 |  | 13
G | 6 | 1
8 |  | 14
0 |  | 4
A | 4 | 0
0 |  | 4
7 |  | 10
C | 3 | 0
7 |  | 10
0 |  | 5
B | 5 | 1
1 |  | 6
5 |  | 7
E | 2 | 1
6 |  | 8
5 |  | 7
D | 2 | 1
6 |  | 8
+/-3
Figure 11.11

## Slide 120
Worker/Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Ann | A |  |  |  |  |  |  | C |  |  | F |  |  | 
Peter | B |  |  |  |  | D |  |  |  |  |  |  |  | 
Fred |  |  |  |  |  | E |  | G |  |  |  |  |  | 
Figure 11.12

## Slide 121
Worker/Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Ann | A |  |  |  |  | D |  | C |  |  | F |  |  | 
Peter | B |  |  |  |  |  |  |  |  |  |  |  |  | 
Fred |  |  |  |  |  | E |  | G |  |  |  |  |  | 
Figure 11.13

## Slide 122
Worker/Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Ann | A |  |  |  |  |  |  | C |  |  | F |  |  |  | 
Peter | B |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Fred |  |  |  |  |  | E |  | D |  | G |  |  |  |  | 
Figure 11.14

## Slide 123
Task 1
Day 1
Task 2
Day 1
Task 3
Day 1
Task 4
Day 2
Task 5
Day 3
Alex
Beth
Alex
Alex
Beth
Figure 11.15

## Slide 124
Task 1
Day 1
Task 2
Day 2
Task 3
Day 2
Task 4
Day 3
Task 5
Day 4
Alex
Beth
Alex
Alex
Beth
Figure 11.16

## Slide 125
Planning
and organizing
Defining the goal
Monitoring and controlling
Execution
Input
Results
- Measure deviation
- Corrective actions
1
2
3
4
Figure 12.1

## Slide 126
Control variables
Time
Risk
Cost
Scope
Quality
Benefits
Figure 12.2

## Slide 127
Schedule
Actual progress
Time
Activities
Figure 12.3

## Slide 128
Time
Costs
Time
Accumulated
costs
S-curve
Figure 12.4

## Slide 129
EV
PC
AC
BAC
t3
Time
Accumulated
costs
t1
t2
Figure 12.5

## Slide 130
EV
PC
AC
BAC
t3
Time
Accumulated
costs
t2
Figure 12.6

## Slide 131
EV
PC
AC
BAC
tp
Time
Costs
t0
EV
PC
AC
BAC
tp
Time
Costs
t0
PC
EV
AC
BAC
tp
Time
Costs
t0
EV
PC
AC
BAC
tp
Time
Costs
t0
PC
EV
AC
BAC
tp
Time
Costs
t0
PC
EV
AC
BAC
tp
Costs
t0
# 1
# 2
# 3
# 4
# 5
# 6
Figure 12.7
Time

## Slide 132
PC
EV
AC
20
weeks
Costs
Time
12 weeks
2,200,000
2,000,000
1,800,000
BV
SV
CV
Time delay
t0
Figure 12.8

## Slide 133
EV
PC
AC
10 weeks
Costs
Time
1,000,000
600,000
500,000
5 weeks
400,000
CV
Figure 12.9

## Slide 134
Activity/Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Teambuilding |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pilot study |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Defining scope/WBS |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Defining requirements |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Designing system |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Developing system |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Testing and implementing |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Training |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Figure 12.10

## Slide 135
Opportunities
Threats
Figure 13.1

## Slide 136
Organization
Management
Goals and framework
Technology
Plans/estimates
Interfaces
Contracts
Responsibility
Internal
risks
Politics
Laws and regulations
Media
Currency
Environment
Customers
Market
Culture
Competition
External
risks
Strike
Bankruptcy
Virus (Covid-19)
Natural disaster
Earthquake
Sabotage
Special events/ accidents
Extreme
risks
More difficult to handle and control
Figure 13.2

## Slide 137
High
Low
Time
Initiation phase
Planning phase
Execution
phase
Termination phase
Risk and uncertainty
Cost of changes
Figure 13.3

## Slide 138
Figure 13.4

## Slide 139
Naïve
Novice
Normalized
Natural
Level 4
Level 2
Level 3
Level 1
Figure 13.5

## Slide 140
Effective
risk management
Methods and processes
Tools and
techniques
Experience and
knowledge
Organizational culture
Figure 13.6

## Slide 141
Plan
Risk
identification
Risk analysis
Risk strategy
(action)
Follow up and
control
Stage 1
Stage 2
Stage 3
Stage 4
Stage 5
Communication and documentation
Figure 13.7

## Slide 142
Team members
leave the project
Better jobs other places
Poor results
Burned out
Negative work environment
A lot of overtime
Unrealistic expectations
Conflicts
Higher salary
New challenges
Low motivation
Low commitment
Bullying
Figure 13.8

## Slide 143
Significant
Significant
Significant
Minor
Minor
Minor
Critical
Critical
Critical
Consequence
Probability
High
Medium
Low
High
Medium
Low
Figure 13.9

## Slide 144
1
2
3
4
5
1
4
6
8
10
3
6
9
12
15
4
8
12
16
20
5
10
15
20
25
1
2
3
4
5
1
2
3
4
5
Score
Very low
Low
Moderate
High
Very high
Very low
Low
Moderate
High
Very high
Probability
Consequence
Figure 13.10

## Slide 145
Significant
Significant
Significant
Minor
Minor
Minor
Critical
Critical
Critical
Negative Consequence
Probability
High
Medium
Low
High
Medium
Low
Critical
Significant
Minor
Critical
Significant
Minor
Critical
Significant
Minor
High
Medium
Low
Positive Consequence
Figure 13.11

## Slide 146
Negative Consequence
Probability
High
Medium
Low
High
Medium
Low
High
Medium
Low
Positive Consequence
2
1
4
5
6
7
8
9
10
3
Figure 13.12

## Slide 147
Negative Consequence
Probability
High
Medium
Low
High
Medium
Low
High
Medium
Low
Positive Consequence
1
5
6
8
10
3
1
3
10
6
5
8
Figure 13.13

## Slide 148
Cost
Time
Quality
Figure 14.1

## Slide 149
Start
End
Time
Project
Define success criteria
Evaluation of
success
Client use of the project results
Figure 14.2

## Slide 150
Figure 14.3
Project owner’s responsibility
Project manager’s responsibility
Stage 1
Stage 2
Stage 3
Benefits planning
Benefits monitoring
Benefits
realization

## Slide 151
Figure 14.4
Benefits
(value)
Time
Expected result
Typical result
Break even
t1
t2
t3